## Slide 1: Project: The implications of replacing corporate tax with a cash flow tax
Alignment with e61 USP
Opportunity to improve and empower the debate on a live policy question using high-quality research.
Policy area is economically large and is an active area of research.
Existing microdata insights are limited, so we can make a large and unique contribution to the debate using microdata.
Will we learn something meaningful?
Yes, the project will close a knowledge gap around the economic outcomes of corporate taxation, and the relative economic benefits of a cash-flow tax reform.
Using microdata allows us to better understand the heterogeneity of any reform and explore first order transitional questions that CGE models struggle with.

## Slide 2: Policy questions answered by the project
Question: What would be the implications of replacing the corporate tax with cash flow tax in Australia?
Why do we care?
Significant slowdown in productivity growth in Australia, with concerns the tax system is contributing to this slowdown.
  Tax may not be the main driver, but the relative taxation of corporations affects investment decisions and entry into the Australian market.
Replacing the corporate tax system with a cash flow tax has been well canvassed by economists and regularly recommended for nearly 30 years.
  But it has failed to get much play in public – due to unclear communication of the issues, and weak empirical evidence.
This project will be focused on adding to the evidence around such a reform using microdata, and then cleanly communicating the results to support appropriate reform.

## Slide 3: Research questions
There are three key areas where evidence on a cash-flow tax is scant:
How would a revenue-neutral cash-flow tax change the tax treatment of different types of firms in Australia? How does this treatment interact with imputation (i.e. would this involve the end of franking credits)?
What would be the overall, and distribution of, investment responses to the introduction of a cash flow tax? How would this change the estimate of the revenue-neutral tax rate needed in the long-run?
How would different transitional arrangements impact on different firms and influence the governments bottom-line during the transition.

## Slide 4: Project details
Project team (names and FTE): TBC. Initial scoping team is: Aaron Wong (X days/week), Matt Nolan (X days/week), Ewan Rankin (oversight, no time requirement), and Lachlan Vass (oversight, no time requirement). If we move past the initial stylised facts into broader modelling, additional people may be required. Especially if McKinnon prioritises this direction in their own tax work.
External collaborators: Early in the project will reach out to the Treasury Tax Frameworks Unit. Also keen to discuss the project with Petr Sedlacek (UNSW) and TTPI given their work in this space. Have already discussed with Chris Murphy (Murphy Economics) who has been responsible for most CGE modelling on the issue – and has offered us free use of his model for this project. Also discussed this with Viva Hammer with regards to the 2017 US tax reforms.
Start date: 10/8/2026
End date: 15/2/2028 (if the project continues through to policy reporting)

## Slide 5: Potential outputs
Outputs: Only high-level outputs are noted – micronotes and engagement kept separate. |  | 
Output | Date | Notes
Research Note 1: Forward looking corporate tax rates and cash flow tax | ~Dec 2026 | Use microdata and a tax model in datalab to calculate tax rates, and the cash flow tax counterfactual.
Research Note 2: Transitional effects of a cash flow tax | ~Jan 2027 | Use microdata to talk about different cash flow tax rules, their impact on revenue, and their impact on firms
Research Note 3: Investment effects of a cash flow tax | ~June 2027 | Estimated investment response to the change in the UCC from a cash flow tax – discuss different imputation rules.
Tool: Corporate tax calculator | ~Sep 2027 | Online tool to illustrate forward looking ETRs
Policy report: The case for corporate tax reform – a cash flow tax? | ~Feb 2028 | Policy report summarising results and literature, with assessment of potential reform.

## Slide 6: Work to first stop-go
Internal policy document on cash flow taxation (underway): The purpose of this document is to describe the rationale and purpose of a cash flow tax, and outline the existing literature.
External consultation on cash flow tax (underway)
Internal presentation: Facts about cash-flow and liquidity constraints for Australian firms – combine microdata work with a summary of (largely RBA) papers.
Micronote “The characteristics of business cash-flow”: Replicate Grozinger (2023) and evaluate the cash surplus figure as a cash-flow measure. Describe the longitudinal properties of this data, and the characteristics of firms with large cash flow (and conversely large depreciation expenses).
plus61: (TBD based on insights)
At this stop-go there is no work on cash-flow tax yet. At this stage determine whether we want to build a tax calculator for corporate tax in datalab.
  If yes move to progressing the first research note. If no, pause project.